## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 6 | DAY 5 | SPRINT REVIEW
DAN | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 10 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 5 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 6 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 4 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 |  | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 |  | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 |  | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 |  | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 |  | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 |  | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 |  | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 |  | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 |  | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 |  | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 |  | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 |  | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 |  | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 |  | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 |  | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 25 | 18 | 14

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
DAN
UML | 3 | Dan | Completed | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Debugging (He did this prior to knowing he was going to corporate) | 2 | Dan | Completed | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RIYAD
Reading through requirements | 1 | Riyad | Completed | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Debugging Routing | 3 | Riyad | Completed | 3 | 0.5 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 0 | 0 | 1 | 0
Routing Code to visit all locations | 4 | Riyad | Completed | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 2 | 1 | 0 | 0
Dimension Address Bug | 2 | Riyad | Completed | 2 | 0 | 0 | 0 | 0 | 0.05 | 1 | 1 | 0 | 0 | 0 | 0
GUI Bugs | 3 | Riyad | Completed | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0.5 | 0
DYLAN
Reading through requirements | 1 | Dylan | Completed | 1 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Bug fixing the neighborhood size (Dimensions) | 2 | Dylan | Completed | 1 | 0 | 0 | 0 | 1 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
Redocumenting AddressGenerator | 2 | Dylan | Completed | 1 | 0 | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0
Units of Time Implementation | 3 | Dylan | Completed | 3 | 0.5 | 0.5 | 1 | 0.5 | 1 | 0 | 0 | 0 | 0.5 | 1 | 2
Bug Fixing GUI and Route | 2 | Dylan | Completed | 2 | 0.5 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Updating User Requirements | 2 | Dylan | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.25
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 24 | DAY 1: 3.5; DAY 2: 4; DAY 3: 2; DAY 4: 3.5