## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 6 | DAY 5 | SPRINT REVIEW
DAN | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 10 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 5 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 6 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 4 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 |  | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 |  | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 |  | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 |  | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 |  | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 |  | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 |  | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 |  | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 |  | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 |  | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 |  | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 |  | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 |  | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 |  | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 |  | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 25 | 18 | 14

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART - TEAM DylanDanRiyad Sprint Five
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | SPRINT REVIEW
DAN
Reading through requirements | 1 | Dan | Completed | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Observer Design Pattern | 2 | Dan | Completed | 2 | 0.5 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0
Strategy Design Pattern | 2 | Dan | Completed | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Factory Design Pattern | 5 | Dan | Completed | 3 | 1 | 0.5 | 1 | 1 | 0 | 0 | 0.5 | 0
Routing GUI | 3 | Dan | Completed | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0.5 | 2
Updating UML | 2 | Dan | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0
TEAM MEETING (GO OVER PRESENTATION) | 1 | Dan | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0
RIYAD
Reading through requirements | 1 | Riyad | Completed | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Truck return to distribution after deliveries | 2 | Riyad | Completed | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
GUI For Which Route | 3 | Riyad | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0.5 | 0 | 0
Make address flexible | 1 | Riyad | Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Real Time based on route length and speed | 4 | Riyad | Completed | 3 | 1 | 0 | 0 | 0 | 1 | 1 | 1.5 | 0
DYLAN
Reading through requirements | 1 | Dylan | Completed | 1 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Updating GUI Window Size | 1 | Dylan | Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reading into Factory Design | 1 | Dylan | Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0
Multiple Orders per address | 3 | Dylan | Completed | 3 | 0.5 | 0.5 | 1 | 0.5 | 1 | 0 | 0 | 0
Constructing Chip and Drink Order Code | 2 | Dylan | Completed | 1 | 0 | 0 | 1 | 0.5 | 0.5 | 0 | 0 | 0
Constructing Sandwich Order Code | 3 | Dylan | Completed | 2 | 0.5 | 0.5 | 1 | 1 | 0 | 0.5 | 0 | 0
TEAM MEETING (GO OVER PRESENTATION) | 1 | Dylan | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0
Updating User Requirements | 2 | Dylan | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 30 | 8.5 | 8.5 | 7.5 | 4