## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 6 | DAY 5 | SPRINT REVIEW
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 10 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 5 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 6 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 4 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 |  | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 |  | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 |  | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 |  | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 |  | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 |  | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 |  | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 |  | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 |  | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 |  | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 |  | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 |  | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 |  | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 |  | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 |  | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 25 | 18 | 14

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | SPRINT REVIEW
Dan
Modify Priority Queue | 2 | Dan | Completed | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Display a simulation of the truck | 5 | Dan | Completed | 6 | 1 | 0.2 | 0.2 | 1 | 2 | 0.5 | 0.5 | 0 | 1
Code Blending | 1 | Dan | Completed | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5
Task
Dylan
Generating Random Times | 3 | Dylan | Completed | 3 | 0.5 | 0.5 | 1 | 1 | 1 | 0.2 | 0 | 0 | 0
Sprint Backlog | 1 | Dylan | Completed | 1 | 0 | 0 | 0.1 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5
UML | 2 | Dylan | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1.5
Task
Riyad
Compute Route | 5 | Riyad | Completed | 5 | 1 | 0.5 | 1 | 1.5 | 0 | 1 | 2 | 2 | 2
Reading and Refactoring Code | 1 | Riyad | Completed | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 19.1 | DAY 1: 3.1; DAY 2: 1.7; DAY 3: 2.3; DAY 4: 3.7; DAY 9: 5.5 | 0